## Sheet1
System Name: HaponGO: Japanese Language Learning App
Members:
Cataos, Felraine Kyle (G5)
Agravante, Rei Samson (G6)
Sugimoto, Kinka (G5)
Statuses |  | Todo
In-Progress
Done
On-hold
[5 empty] | February |  |  |  | March |  |  |  | April |  |  |  | May
Tasks | Assignee | Date Started | Date Finished | Status | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4
1.0 Concept
1.1 Define Project Scopes & Objectives
1.2 Define User Requirements
1.2.1 Define Functional Requirements
1.2.2 Define Non-Functional Requirements
1.3 Develop Project Plan
1.4 Brief Web Development Team
2.0 Website Design
2.1 Create Wireframes
2.1.1 Design wireframe for user dashboard
2.1.2 Design wireframe for lessons
2.1.3 Design wireframe for English-Japanese Dictionary
2.1.4 Design calligraphy practice wireframe
2.1.5 Design wireframe for leaderboard
2.1.6 Design wireframe for payment module
2.2 Create UI Screens
2.2.1 Design user dashboard UI
2.2.2 Design user dashboard UI
2.2.3 Design English-Japanese dictionary UI
2.2.4 Design calligraphy practice UI
2.2.5 Design leaderboard UI
2.2.6 Design payment module UI
3.0 Website Development
3.1 Backend Development
3.1.1 Setup Database
3.1.2 Setup authentication system
3.1.3 Develop login/signup
3.1.4 Develop user progress tracking
3.1.5 Develop leaderboard system
3.1.6 Integrate payment module
3.2 Frontend Development
3.2.1 Develop UI for login/signup
3.2.2 Develop user dashboard UI
3.2.3 Develop lesson screen UI
3.2.4 Develop dictionary UI
3.2.5 Develop calligraphy practice UI
3.2.6 Develop leaderboardUI
3.2.7 Develop payment UI
4.0 Roll out
4.1 Deploy web and mobile application
4.2 Test Android Compatibility
4.3 Test Backend Compatibility
5.0 Support
5.1 Monitor System Performance
5.2 Enhance Security & Privacy measures