## Sheet1
System Name: HaponGO: Japanese Language Learning App
Members:
Cataos, Felraine Kyle (G5)
Agravante, Rei Samson (G6)
Sugimoto, Kinka (G5)
Statuses |  | Todo
In-Progress
Done
On-hold
[5 empty] | February |  |  |  | March |  |  |  | April |  |  |  | May
Tasks | Assignee | Date Started | Date Finished | Status | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4
1. Gantt Chart Creation | Felraine Kyle Cataos | 2025-03-10 | 2025-03-10 | Done
2. Functional & Non-Functional Requirements | Felraine Kyle Cataos, Kinka Sugimoto, Rei Samson Agravante | 2025-03-10 | 2025-03-10 | In-Progress
3. ERD | Felraine Kyle Cataos, Kinka Sugimoto, Rei Samson Agravante | 2025-02-14 | 2025-02-14 | Done
4. Wireframe
4.1 Wireframe Web
4.1.1 Login Wireframe | Kinka Sugimoto | 2025-02-17 | 2/30/2025 | Done
4.1.2 Create Account Wireframe | Kinka Sugimoto | 2025-02-17 | 2/30/2025 | Done
4.1.3 Dashboard Wireframe | Kinka Sugimoto | 2025-02-17 | 2/30/2025 | Done
4.1.4 Profile Wireframe | Felraine Kyle Cataos | 2025-02-17 | 2/30/2025 | Done
4.2 Mobile Wireframe
4.2.1 Login Wireframe | Rei Samson Agravante | 2/30/2025 | 2025-03-17 | In-Progress
4.2.2 Create Account Wireframe | Rei Samson Agravante | 2/30/2025 | 2025-03-17 | In-Progress
4.2.3 Dashboard Wireframe | Rei Samson Agravante | 2/30/2025 | 2025-03-17 | In-Progress
4.2.4 Profile Wireframe | Felraine Kyle Cataos | 2/30/2025 | 2025-03-17 | In-Progress